## ProjectSchedule
PrivaLens: Automated Web Privacy & Regulatory Compliance Scanner
TIET Patiala - UCS503 Software Engineering |  | Project Start: | 2026-08-03
Project Lead: Naman Arora (Roll No: 1024160029) |  | Today: | 2026-10-17
|  | Display Week: | 11
TASK | ASSIGNED TO | PROGRESS | START | END | DAYS
Phase 1: Inception & Proposal Setup
Problem Definition & DPDP/GDPR Regulatory Research | Ishmanjot Singh | 100% | 2026-08-03 | 2026-08-08
System Architecture & Microservices Specification | Prabhrajwin Singh | 100% | 2026-08-07 | 2026-08-13
Git Repository Setup & CI/CD GitHub Pages Deployment | Naman Arora | 100% | 2026-08-10 | 2026-08-15
Pitch Slide Deck Design & Presentation Materials | Naman Arora | 100% | 2026-08-14 | 2026-08-19
Formal LaTeX Project Proposal & TikZ Architecture Modeling | Naman Arora | 100% | 2026-08-18 | 2026-08-23
Phase 2: System Modeling & Technical Design
UML Use Case Diagram Engineering in TikZ | Naman Arora | 100% | 2026-08-24 | 2026-08-29
3-Level Data Flow Diagrams (DFD Level 0, 1, 2) Design | Naman Arora | 100% | 2026-08-25 | 2026-08-30
PostgreSQL Relational Database Schema & Entities Design | Prabhrajwin Singh | 100% | 2026-08-28 | 2026-09-02
Legal Clause Taxonomy & Discrepancy Matrix Definition | Ishmanjot Singh | 100% | 2026-08-30 | 2026-09-04
Project Master Schedule & Gantt Tracking Setup | Naman Arora | 100% | 2026-09-02 | 2026-09-06
Phase 3: Engine Prototyping & Backend Core
Headless Crawler & Network Traffic Interceptor (Puppeteer) | Prabhrajwin Singh | 100% | 2026-09-07 | 2026-09-18
Asynchronous Job Queue & Worker Pipeline (Redis/Bull) | Prabhrajwin Singh | 100% | 2026-09-14 | 2026-09-24
Privacy Policy Scraper & NLP Parser (SpaCy Pipeline) | Ishmanjot Singh | 100% | 2026-09-12 | 2026-09-25
Frontend UI Dashboard & Scan Submission (Next.js/Tailwind) | Naman Arora | 100% | 2026-09-09 | 2026-09-28
Prototype Integration Milestone & Mid-Evaluation Prep | Naman Arora | 100% | 2026-09-26 | 2026-10-04
Phase 4: Compliance Scoring & Advanced Auditing
Automated PII & Cookie Exfiltration Detection Engine | Prabhrajwin Singh | 100% | 2026-10-05 | 2026-10-14
Policy-to-Runtime Discrepancy Matching Algorithm | Ishmanjot Singh | 90% | 2026-10-09 | 2026-10-18
Interactive Compliance Scorecard & Remediation Portal | Naman Arora | 85% | 2026-10-12 | 2026-10-22
Automated PDF Compliance Audit Report Generation | Naman Arora | 70% | 2026-10-16 | 2026-10-24
REST API Hardening, Error Handling & Logging Middleware | Prabhrajwin Singh | 30% | 2026-10-18 | 2026-10-25
Phase 5: Testing, Documentation & Final Delivery
System Integration & End-to-End Crawler Testing | Prabhrajwin Singh | 0% | 2026-10-26 | 2026-11-04
NLP Model Evaluation (Accuracy, Precision & Recall Benchmarks) | Ishmanjot Singh | 0% | 2026-10-30 | 2026-11-08
Production Dockerization, Cloud Deployment & UI Polishing | Naman Arora | 0% | 2026-11-03 | 2026-11-13
Comprehensive LaTeX Final Project Report Authoring | Naman Arora | 0% | 2026-11-08 | 2026-11-17
Final Viva Presentation Deck & Project Demonstration | Naman Arora | 0% | 2026-11-12 | 2026-11-20
Note on H6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.